## DIP project plan
Note the below is a high level illustrative outline only. Specific tasks, dates etc will be project dependent and should clearly lay out how tasks are planned, agreed, completed, verified and signed off.
A gantt chart to the right which sets out the project activities would be advisable
| Current date | 2025-11-05 | [8 empty] | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12
| Task name | Start date | End date | Status | Proportion of time elapsed | Overdue flag | Owner | Stakeholders | Other parties | Dependencies | [w/c DATE] | [w/c DATE] | [w/c DATE] | [w/c DATE] | [w/c DATE] | [w/c DATE] | [w/c DATE] | [w/c DATE] | [w/c DATE] | [w/c DATE] | [w/c DATE] | [w/c DATE]
Milestones
Milestone 1
Milestone 2
Milestone 3
Milestone 4
1 | Contracting and documentation
1.1 | Appoint third party to carry out DIP | 2026-01-01 | 2026-01-14 | Not started | 0% | bar: Week 1 to Week 2
1.2 | Confirm resources for required activities, including processing, review and technical sign-off |  |  |  | #DIV/0!
1.3 | Put in place contracts including negotiation on commercial terms |  |  |  | #DIV/0!
1.4 | Put data sharing agreements in place as needed for third parties |  |  |  | #DIV/0!
1.5 | Agree and document roles and responsibilities within DIP |  |  |  | #DIV/0!
1.6 | Agree how activities will be managed, how progress will be monitored and and how updates will be provided |  |  |  | #DIV/0!
1.7 | Document changes made to data and processes to be followed in the future |  |  |  | #DIV/0!
1.8 | Document any recommended future actions for further improvement |  |  |  | #DIV/0!
2 | Data changes and testing
2.1 | If relevant, data transferred to third party for review. Note that where a third party separate to the administrator, or a separate team within the third party administrator business is carrying out work, actions on reviewing the data received and understanding it / time for queries to the administration team should be expected. |  |  |  | #DIV/0!
2.2 | Testing of data to assess gaps |  |  |  | #DIV/0!
2.3 | Advice to Trustee on specific work to be carried out to address gaps. To include decisions to be made by Trustees and any assumptions expected to be made. |  |  |  | #DIV/0!
2.4 | Formal confirmation of decisions made provided by the Trustee |  |  |  | #DIV/0!
2.5 | Phase 1 of data cleanse activities [set out actions to be taken] |  |  |  | #DIV/0!
2.6 | Phase 2 of data cleanse activities [set out actions to be taken] |  |  |  | #DIV/0!
2.7 | Updated data returned to administration team |  |  |  | #DIV/0!
2.8 | Updated data uploaded to administration system |  |  |  | #DIV/0!
2.9 | Testing of uploaded data by the administrator |  |  |  | #DIV/0!
2.1 | Updated data signed off by the administrator |  |  |  | #DIV/0!
3 | Updating data
3.1 | Updates completed on data taking into account Trustee decisions |  |  |  | #DIV/0!
3.2 | Review and sign off procedures on data updates |  |  |  | #DIV/0!
3.3 | Output data is signed off by administrator or third party |  |  |  | #DIV/0!
3.4 | As appropriate, summary impacts provided to the Trustee to outline the impact of the change |  |  |  | #DIV/0!

## DIP requirements
Note the below sets out examples only. Requirements should be based on scheme specific data analysis, data and operational requirements, and managerial decision making
Ref | Data requirement | Information | Number of records impacted | Number of members impacted | Risk assessment | Impact assessment | Action | Owner | Stakeholders | Other parties | Phase | Start date | Target completion date | Impact on BAU processes? | BAU impact assessment | BAU Action | BAU Owner | BAU Stakeholders | BAU other parties | BAU Start date | BAU target completion date
1.1 | Data issue 1
1.2 | Data issue 2
1.3 | Example: Missing contribution data | Contribution data is missing from member records. This is important for death in deferment benefits | 200 deferred records | 200 deferred members | Low risk | Only required for deferred members below normal retirement age, and in an unlikely event | Use file scraping technology to source required data and add to member records | Project Lead | Trustees, Administrator, Risk Transfer Adviser | Legal advisers, Scheme Actuary | 2 | 2026-01-01 | 2026-01-31 | Yes | Collection of contributions data for active members | Automation of monthly data collection to add monthly contribution data to total contributions data field | Systems team lead | Trustee, administrator | N/A | 2026-01-01 | 2026-01-31

## Lists (hidden)
Not started | Overdue
In progress
Complete